## Inventory_Execution_Tracker
Part Number | Part Description | Revision | Supplier | Program / Build | Required Qty | Need Date | On-Hand Qty | In-Transit Qty | Open PO Qty | Total Available | Shortage / Excess | Lead Time (weeks) | Risk Level | Owner | Last Supplier Update | Notes / Next Action
HNS-ASSY-010 | Wiring Harness Assembly | B | Supplier B | Pilot Build P2 | 10 | 2026-03-09 | 3 | 2 | 5 | 10 | 0 | 6 | RED | Nisarga | 2026-02-06 | Await PO ack; verify connector rev
MTR-48V-001 | 48V BLDC Motor - Actuation | A | Supplier A | Proto Build P1 | 4 | 2026-03-24 | 1 | 1 | 2 | 4 | 0 | 12 | YELLOW | Nisarga | 2026-02-05 | Confirm ship date; check partial shipment
PCB-FC-020 | Control Board (Flight/Control) | C | Supplier C | Proto Build P1 | 2 | 2026-04-08 | 0 | 0 | 2 | 2 | 0 | 14 | GREEN | Nisarga | 2026-02-02 | Risk review with supplier; confirm capacity
Formulas:
Risk Level = IF(OR([Need Date]="",[Lead Time (weeks)]=""),"",IF([Shortage / Excess]<0,"RED",IF([Need Date]-TODAY()<[Lead Time (weeks)]*7,"YELLOW","GREEN")))

## Instructions
How to use this tracker (quick):
1) Fill in Part Number, Description, Supplier, Program/Build, Required Qty, Need Date, and Lead Time.
2) Update On-Hand, In-Transit, and Open PO Qty (pull from ERP/SAP exports if available).
3) Total Available, Shortage/Excess, and Risk Level auto-calculate.
4) Review RED/YELLOW items daily/weekly; capture next actions and last supplier update.
Notes:
- ERP/SAP remains the system of record. This tracker is for execution visibility (risk + next actions).
- You can override Risk Level via dropdown if needed (e.g., known quality risk).

## Lists
Risk Levels
GREEN
YELLOW
RED